## Sheet1
| CRC32 calculated value in STM and python shall be same | DONE
| implement CRC32 calc and append in python | DONE
| test LED blinking with CRC32 Send the LED delay from python and verify CRC in STM, if CRC matches then modify the delay of LED Data reception in UART interrupt mode | DONE
| Establish Acknowledgement based communicaton | DONE
| Create Duplex communicaation b/w STM_BL and python send command from python and STM executes and sends response back | DONE
| implement multibyte data transfer to STM in python | DONE
| implement multibyte data reception in STM | DONE
| implement memwrite in bootloader | DONE |  |  |  | Bootloader commands
| TEST memwrite by sending 10 bytes of contineous data | DONE |  | DONE | 0xB1 | Bootloader Version
| implement memory clear in STM | DONE |  | DONE | 0xB2 | Cchip Identification Number
| test by clearing some memory address snet in python | DONE |  | DONE | 0xB3 | Erase Application | Erases all the Application Memory
| Implement Jump to bootloader command in python | DONE |  | DONE | 0xB4 | Flash Application
[5 empty] | 0xB5 | Check Application Integrity | Calculate the CRC of Application and Verify it with CRC already STORED
Objective | transfer a bin througn memwrite in python | DONE |  | DONE | 0xB6 | Jump to Application
|  |  | 1 |  | 4
|  |  | CMD | NO.OF.PACKTES - 2Bytes | CRC | DONE
|  |  | ACK |  |  | DONE
|  |  | CMD | LEN.NEXT.PACK - 2BYTES | CRC | DONE
|  |  | ACK |  |  | DONE
|  |  | CMD | PACKET | CRC | DONE
|  |  | ACK |  |  | DONE
|  |  | CMD | LEN.NEXT.PACK | CRC | DONE
|  |  | ACK |  |  | DONE
|  |  | CMD | PACKET | CRC | DONE
|  |  | ACK |  |  | DONE
|  |  | CMD | END.PACK | CRC
End pack is length of 4 bytes with CRC of complete BIN file, Similaryly STM also calculates the CRC of whole data in PFLASH and sends it to Python. Python Compares the CRC with calculated CRC and confirms if Application is flashed successfully.